## Sheet1
Task | P | Priority | Assigned to | Est Hours | Logged Hours | Status
Basic Board HTML & Positioning CSS | 0 | Top
Advanced CSS positioning (relative) | 1 | Very High
JS to use touch buttons to input values, instead of keyboard | 1 | Very High
way to store and load different boards | 1 | Very High
Add native functionality (Shake Gesture - to reset board) | 1 | Very High | John Borges |  |  | In Progress
Add Menu and Options | 2 | High
Dynamic CSS for selections (Boarder for current selection, background-color for related fields) | 2 | High
JS to check for solved | 2 | High | John Borges |  |  | In Progress
JS Timer | 3 | Moderate | John Borges |  |  | In Progress
Game History/Statistics (Records, fastest time etc) | 3 | Moderate
Add Note feature (User Manually and remove notes) | 3 | Moderate
Smart Notes Feature (Auto Populate all note, Auto Update notes as values change) | 4 | Low
Feature to toggle input between selecting Cell then button and button then cells | 4 | Low
Video Demo
PhoneGAP Deployment???